## Top
Enhancement | TSI | Impact | Date Raised | No TSI | Progress | Timescale
Ability to record events and training | Various | Medium |  | 14 | Not in scope for initial rebuild - priority for later development | tbc
Automatically import data from the Saltire web site into Milo | D&G | High | 2014-03-01 | 13 | Potential to set up via API following implementation | tbc
Get VZ data automatically into Milo | Glasgow | High | 2014-01-01 | 11 | In scope, but standard opportunity feed takes priority | Next phase (Q2-Q3)
When search for a record and it is on page 20 of the results. Closing the record returns to page. It should return to the page you left | Orkney | medium |  | 11 | Salesforce global search and 'recent records' view fixes this | At live
Ability to email directly from Milo without having to export | Various | High |  | 11 | Possible - subject to further investigation | tbc
Ability to support mass emails and newsletters | D&G | low |  | 11 | Possible - subject to further investigation | tbc
When adding a new contact Milo may return that the contact already exists. It would be nice to have more details as to where in the system this contact resides | Various | High |  | 10 | Contacts system is being revised - won't get this error message anymore | At live
Ability to import data from OSCR | Various | High |  | 10 | Potential to set up via API following implementation | tbc
Get brief detail of contact when more than one contact is returned by search. This will help in ensuring the correct contact is used | South Lan | High |  | 9 | More detail on contacts returned in global search | At live
When deleting a contact provide links to show what organisation, opportunities, etc. the contact is associated with and provide a means of either deleting or reassigning the relationship | Western Island | High |  | 9 | Can see associations with contact from record | At live
Saltire Challenge Award can be obtained multiple times by a single person but Milo only lets you record this once. Can the challenge section be expanded to include the number of times it has been awarded. | Various | High | 2014-04-01 | 8 | Able to add / amend new fields subject to discussion with MUG | At live
Better volunteer /opportunity matching ie.return all opportunities for all the interests that a volunteer as picked | Aberdeenshire | Medium |  | 8 | Able to add / amend new fields subject to discussion with MUG | tbc
Simplify Episodes and interactions | Various | High |  | 7 | Streamlined system in development; removes Episode layer and focuses on interactions | At live
Recording of Historical data fields e.g. finance staff numbers etc. | Glasgow | High | 2012-08-01 | 6 | System in development; allows recording of key data over different years | At live
Make why Volunteer Multi Choice | East Ren | medium |  | 6 | Being done | At live
When an organisation is marked as ceased. Their opportunies should be changed to Archived automatically | SCVO | High |  | 6 | Currently investigating | tbc
Make reporting easier for the novice | Various | High |  | 6 | Salesforce allows creation of dashboards that will provide easy real-time reporting on common areas | At live
Ability to add attachments to organisation records | South Lanarkshire | High |  | 6 | Able to add notes and attachments direct to org record (subject to storage space) | At live
Automatic alerts to TSI and VIO to update opportunity 14 days in advance of the publish end date. | Glasgow | medium |  | 6 | Currently investigating | tbc
Ability for better support for TSI specific projects to be recorded in Milo | Various | High |  | 6 | Able to add / amend new fields subject to discussion with MUG | At live
Improve the way of identifying social enterprise organisations | Various | medium |  | 6 | Able to add / amend new fields subject to discussion with MUG | At live
Script/Button to remove all deceased contact records | D&G | medium | 2012-08-01 | 5 | Investigating ways to do this - possibly using bulk upload | At live
Quick input screen for organisations and contacts records | Various | medium | 2013-01-01 | 5 | Quick Create' app allows you to add org or contact with minimum of 1 field | At live
Add reviewed date next to the start date for volunteer opportunities | D&G | medium | 2014-04-01 | 5 | Able to add / amend new fields subject to discussion with MUG | At live
Deduplication of contacts records | West Lothian | High |  | 5 | Could be done with bulk upload - other alternative is to cleanse pre-migration using edit dates | tbc
TSI to have the ability to control what fields are collected i.e., set their own mandatory fields | Various | High |  | 5 | Subject to discussion with MUG - can add / amend fields (possibility to do this at a more granular level with views / roles) | tbc
Improve look and feel and work flow | Various | High | 2012-08-01 | 5 | More responsive UI, able to move between sections more quickly and click into 7 most recent items | At live
Ability to copy opportunities between organisations | Glasgow |  |  | 5 | New - ability to clone opps and change all details including related org | At live
Provide the ability to have records open in multiple tabs | Western Island | medium |  | 5 | Can have multiple tabs open, but better navigation reduces need for this | At live
Ability to select which job cards required to be printed | Various | High |  | 5 | Currently investigating | tbc
Provide crosstab reporting | Various | medium |  | 5 | Reporting is changing - possible to create custom dashboards | tbc
Ability to record what school a young person attends | WL | medium |  | 5 | Able to add / amend new fields subject to discussion with MUG | At live
TSI to have the ability to display what fields should be available for input | Various | High |  | 5 | Custom views | tbc
Ability to edit records from reports | Fife | medium | 2014-01-01 | 4 | Depends on reporting access - further work pending | tbc
Statutory Organisation need to be able to change publish to local directory | Orkney | Medium | 2014-06-01 | 4 | Able to add / amend new fields subject to discussion with MUG | At live
Ability for organisation to manage there own details and opportunities | Various | High |  | 4 | Will be possible using web forms, but not in scope for initial build | Next phase (Q2-Q3)
Ability for volunteers to update their detail | Various | Low |  | 4 | Will be possible using web forms, but not in scope for initial build | Next phase (Q2-Q3)
Make the search more intuitive and user friendly allowing for spelling mistakes and support for wild cards | Aberdeenshire Western Islands | medium |  | 4 | Global search is more intuitive; ability to use wild cards | At live
Ability to add notes to organisation records | South Lanarkshire | medium |  | 4 | Can already do on current system - improved version on Milo 2 allowing multiple notes and privacy settings | At live
Direct printing of reports without the need to export first | South Lan | low |  | 4 | Depends on reporting access - further work pending | tbc
Automatic email when assign an open/on going interaction to someone else | D&G, Edinburgh | medium |  | 4 | Interaction system being revamped | tbc
Have the abilitity to have another category level for Interactions | South Lan, West Lothian | medium |  | 4 | Interaction system being revamped - possibility to add groupings | tbc
Save and close button as well as the separate save and close buttons | Western Isles, | medium | 2014-01-01 | 3 | Search and recent items on same screen so no need to go back to separate search | At live
Why Volunteer when select Other there should be a text box to enter why | East Ren | High |  | 3 | Fixed | At live
Not to publish organisation details to we web requires unrelated mandatory fields to be answered in the additional profile section. Remove this requirement | Perth | High |  | 3 | Fixed | At live
Ability to record social media links for organisations | Inverclyde, South Lan | medium | 2014-11-01 | 3 | Able to add / amend new fields subject to discussion with MUG | At live
Ability to assign an opportunity to a particular geographic area rather than a fixed location | South Lan | medium |  | 3 | Able to add / amend new fields subject to discussion with MUG | tbc
Improve the look and feel of the iFrames | Various | medium |  | 3 | Better iframes or equivalent will be built using APIs | Next phase (Q2-Q3)
Integration of Outlook with Episodes and Interaction | West Lothian | medium |  | 3 | Interaction system being revamped | tbc
Ability to use a Post Code Look up to complete filling in address fields | West Lothian | medium | 2012-08-01 | 2 | Don't know if feasible but will investigate and cost | tbc
Ability to remove location from an organisation when there is only one location associated with organisation as this is regarded as the main location and cannot be deleted. | Inverclyde, South Lan | High | 2014-01-01 | 2 | Fixed | At live
Create another level over user similar to Basic user but has the ability to edit opportunities or Modify basic user rights to edit opportunities | Edinburgh | medium | 2014-03-01 | 2 | Subject to testing but should be possible with roles | At live
In placement section can only record hours worked on a day by day basis. Need the ability just to record total number of hours worked | Various | High |  | 2 | Able to add / amend new fields subject to discussion with MUG | At live
TSI to be able to define their own dash board | Various | Medium |  | 2 | Plan is to create individual views for TSIs | At live
Allow the unsettling of Saltire award registered. Once this is set and the volunteer record is saved it cannot be changed | South Lan | High |  | 2 | Will have ability to do this | At live
Milo to function fully on in all Browsers | Glasgow | High |  | 2 | Salesforce supports all major browsers | At live
Automatically date and name to all notes fields | Glasgow, South | medium |  | 2 | As standard for organisation notes | At live
Make the publication of new opportunities to VS quicker e.g.. 2 minutes | Glasgow | medium |  | 2 | Work in progress - should be smoother feed (exact timings tbc) | At live
Ability to change the organisation to which an opportunity is assigned | Western Island | High |  | 2 | Will have ability to do this | At live
Automatic email alerts to action owners | South Lan | medium |  | 2 | Interaction system being revamped | tbc
Add another option to are travel expenses paid 'To be discussed' | Glasgow | low |  | 2 | Able to add / amend new fields subject to discussion with MUG | At live
Ability to allow statutory organisations details to be published to web | Orkney | medium |  | 2 | Able to add / amend new fields subject to discussion with MUG | At live
Allow TSI to define what fields are accessible through web services | Inverclyde, South Lan |  |  | 2 | Can do this using APIs | At live
Max age validation should be set higher e.g. 200 | SCVO | medium | 2014-01-01 | 1 | Able to amend field requirements subject to discussion with MUG | At live
Allow partial post codes | Glasgow | Low | 2014-01-01 | 1 | Able to amend field requirements subject to discussion with MUG | At live
Addition of Daytime contact telephone field for contacts e.g. work | D&G, Shetland | medium | 2014-01-01 | 1 | Able to add / amend new fields subject to discussion with MUG | At live
Make LSEN an organisation type and TSI component | SCVO |  | 2014-01-01 | 1 | Able to add / amend new fields subject to discussion with MUG | At live
Ability to edit looks ups in main activities | P&K | low | 2014-01-01 | 1 | Able to add / amend new fields subject to discussion with MUG | At live
Transfer responsibility button currently transfers the organisation and all associated Organisation Contact records to new TSI. As the contacts themselves remain in the old TSI and contacts can be attached to organisations held by other TSIs wouldn’t it be better if the old TSI still retained permissions for their Organisation Contact associations?” | West Lothian | High | 2014-04-01 | 1 | Works differently in new system but will be possible to retain contacts in original TSI (or move if wished) | At live
Add a tab to the contact to see what opportunities they are the main contact for | Edinburgh | medium | 2014-06-01 | 1 | Associated opps shown in contact record | At live
Increase the size of text that can be added to interaction action the limit is currently 250 characters | Edinburgh | medium | 2014-06-01 | 1 | Able to amend field requirements subject to discussion with MUG | At live
Remove restriction that membership date must be in the future when ever you change any of the membership details | South Lan | medium | 2014-07-01 | 1 | Able to add / amend new fields subject to discussion with MUG | At live
Last login date is not always correctly recorded | South Lan | High | 2014-07-01 | 1 | Bug not present in new system | At live
Allow the removal of all locations associated with and organisation. Currently you cannot delete the primary location | Inverclyde, South Lan | medium |  | 1 | Will have ability to do this | At live
Ability for Tsi to make global changes to a particular field | WL |  |  | 1 | Able to add / amend new fields subject to discussion with MUG - global changes will be restricted though | No
TSI to define their own search field filters | Various | medium |  | 1 | Global search is more intuitive; ability to use wild cards | At live
Add opportunity application to published data and available within Milo | Glasgow | low |  | 1 | More info needed - is this to attach documents?
Improve usability of shared document area |  | medium |  | 1 | Document storage changing | tbc
Allow TSI to import data from files | Vairious |  |  | 1 | Bulk import is possible | At live
Conformation of log-out i.e. Are you sure | North Ayrshire |  | 2013-01-01 |  | No - sorry! Password reset is now easier though | No
Main activity field to be displayed in columns | P&K | low | 2014-01-01 |  | Search results screen different - should be customisable | At live
Travel details for an opportunity not available in the opportunity iFrame | South Lan | medium | 2014-07-01 |  | iFrames changing | tbc
Increase the size of text that can be added into the opportunity description fields | South Lan | High |  |  | Able to amend field requirements subject to discussion with MUG | At live
When changing any opportunity details that they are published in a timely manner | Glasgow | medium |  |  | Work in progress - should be smoother feed (exact timings tbc) | At live
Increase the number of characters for training in an opportunity | Glasgow | High |  |  | Able to amend field requirements subject to discussion with MUG | At live
Make the Services Accessed a local lookup | NA | medium |  |  | Won't have local lookups for this but can amend globally - could be addressed by new interaction system or by using notes | NA
Ability to have open actions from closed interactions | South Lanarkshire | medium |  |  | Interaction system being revamped | tbc
Ability to record what services are delivered at a particular location | South Lan | medium |  |  | Able to add / amend new fields subject to discussion with MUG | At live
When publishing an opportunity have a link to a journey planner | Glasgow | low |  |  | Don't know if feasible but will investigate and cost | tbc
Mobile friendly interface |  | low |  |  | Salesforce works on mobile devices | At live